## Sheet1
| Milestone 1 |  | Milestone 2 |  | Milestone 3 |  | Milestone 4
Application | Features | Acceptance Criteria | Features | Acceptance Criteria | Features | Acceptance Criteria | Features | Acceptance Criteria
Call Center Agent App (Android) | Signup and Onboarding | User will be able to Create profile and await approval. User will be able to view approval status. User will be able to send reminder for approval. User will be able to create a profile with basic details. | Dashboard & Performance | User will be able to view Tasks to do. User will be able to view Productivity Numbers User will be able to view Performance Numbers | FAQ & Script Management | User will be able to easily access to scenario based scripts and FAQ | Incremental improvements and bug fixes
| Manage availability / CCA Profile | User will be able to define and update available days and times of call. | Learning Management (Wiki) | User will be able to Access LMS content for self consumption. View all topics, read, tag them to Parents or child while on the call. | Incremental improvements and bug fixes
| Parent Management System | User will be able to View all mapped parents. User will be able to create, view, update parent profile User will be able to create, view, update child profile | Roster | Automated Roster Management and show tentative roaster for upto two working days ahead.
| Roster | User will be able to view the roster for today. User will be able to view quick stats with calls to be made, done, reschedules, failed, etc. User will be able to view view roaster of upto previous 3 months. | Call Routing and Management | User will be able to log Inbound call from parents User will be able to capture call feedback & Notes
| Call Routing and Management | User will be able to make outbound call to parents User will be able to capture call feedback & Notes | Access Recordings | Access Recordings via telephony service provider.
| Automated Roster Algorithn (Only logic) | Algorithm that manages call schedules for each agent. | Incremental improvements and bug fixes
Admin App (Web) | Signup and onboarding of all user types, including CCA, Parents. | User will be able to Add users User will be able to approve/reject CCA signups | Learning Management | Create, Read, Update, Delete new modules for LMS. | Community Moderation | User will be able to moderate content posted by parents. | Incremental improvements and bug fixes
| Parent Management System | User will be able to Add, view, update, delete parents, children and their information. View history of interactions, via call, whatsapp chat. | Access Recordings | Access Recordings via telephony service provider. | Notifications | User will be create and push in-app notification. User can schedule and create custom notifications.
| Roster Management System | User will be able to manage Roster by manually assigning parents to CCAs on daily basis. | Roster Management System (Automated) | User will be able to auto assign roster to CCA and will have the abillity to overright the logic via manual intervention. | Incremental improvements and bug fixes
| Feedback and Notes | User will be able to view aggregate and call level feedback and notes. filter via CCA, date range. | Analytics Dashboard | User will be able to view the following reports. - CCA performance reports (#of days active, # of calls done, dropped, rescheduled, feedback), - Parent Reports (# of Active, Semi-Active, Passive, Unreachable, Unresponsive, etc.) - All reports to be on date ranges.
Incremental improvements and bug fixes
Parent Web App |  |  |  |  | Signup and Onboarding | User will be able to Signup. User will be auto-assigned a CCA, if requested and available. Or admin will be notified. | Access interaction history | User will be able to view interaction history, including calls history (Inbound, Outbound) and whatsapp History
[5 empty] | Profile and Child Profile | User will be able to Create profile of self and children Add images, PII, Interests to profile | Call via VOIP | User will be able to call the assigned CCA. If unanswered or otherwise, user should be able to schedule a call with CCA
[5 empty] | LMS | Use will be able to Access LMS content and mark complete. User will be able to view completed modules, and yet to start modules. | Community chatter | User wil be able to view and post updates on a timeline. like, comment, share on posts. Posts can have an image, text and 3rd party links.
[5 empty] | Trigger Whatsapp Chat | User will be able to Trigger Whatsapp chat from the webapp, when accesing via mobile. | Gamification | User will be able to gather Points basis online activity. User will be able to earn badges based on Assessments
[7 empty] | Identification of Saajhedars | User will be able to apply to become a Saajhedar (CCA) by filling up a survey,